## Overstock Connector
Project Plan - Mind Games
Team: Sales: Scott (stanzillo@netscoretech.com) Project Manager: Vinod (vinod@netscoretech.com) Product Development : Sunil (skancharla@netscoretech.com) NetScore Support : support@netscoretech.atlassian.net | Access: WooCommerce : vinod@netscoretech.com NetSuite : vinod@netscoretech.com
Pending Tasks
Completed Tasks
Go live Risk/Need to take action
Task | Status | Primary Responsibility | Expected Start Date | Expected End Date | Dependencies | Notes
1. Sign off |  | NetScore - Mind Games
Mind Games Sign off with NetScore |  | NetScore - Mind Games
2. Kick off |  | NetScore - Mind Games
NetScore - Mind Games Kickoff Meeting |  | NetScore - Mind Games
3. Access |  | Mind Games
NetSuite and WooCommerce access |  | Mind Games
4. WooCommerce Connector Installation |  | NetScore | 2022-06-06 | 2022-06-17
NetSuite bundle installation |  | NetScore | 2022-06-06 | 2022-06-06
Connector configuration |  | NetScore | 2022-06-07 | 2022-06-07 | Required a meeting with customer for configuration.
Item, Inventory & Price Export |  | NetScore | 2022-06-08 | 2022-06-10 | Required item mapping from Mind Games
Order Import from WooCommerce to NetSuite |  | NetScore | 2022-06-13 | 2022-06-14
Shipments export from NetSuite to WooCommerce |  | NetScore | 2022-06-15 | 2022-06-16
Returns, Refunds & Cancellations from WooCommerce to NetSuite |  | NetScore | 2022-06-17 | 2022-06-17
5. Functionality Testing |  | NetScore | 2022-06-20 | 2022-06-21
NetSuite - WooCommerce Connector Functionality testing |  | NetScore | 2022-06-20 | 2022-06-21
6. Customer UAT |  | Mind Games | 2022-06-22 | 2022-06-23
NetSuite - WooCommerce Connector UAT |  | Mind Games | 2022-06-22 | 2022-06-23
Go Live |  | NetScore - Mind Games | 2022-06-24
Post Go-Live Support |  | NetScore - Mind Games | 2022-06-24 | 2022-06-29
7. Close |  | NetScore - Mind Games | 2022-06-30 | 2022-06-30
Project Feedback & Closure |  | NetScore - Mind Games | 2022-06-30 | 2022-06-30